## Sheet1
|  | Austin | AJ | Final
Iteration 1 | Add Account | 6 hrs | 6 hrs | 6 hrs | 10 | 6
| Submit Project | 12 hrs | 12 hrs | 12 hrs | 10 | 18
| View Pending Projects | 8 hrs | 8 hrs | 8 hrs | 10 | 26
| Evaluate Project | 2 hrs | 3 hrs | 3 hrs | 10 | 29
| Approve Project | 4 hrs | 4 hrs | 4 hrs | 10 | 33
| View Projects | 24 hrs | 24 hrs | 24 hrs | 20 | 57
Iteration 2 | View Project | 12 hrs | 12 hrs | 12 hrs | 20
| Rate Project | 16 hrs | 16 hrs | 16 hrs | 30
| Add Review | 8 hrs | 4 hrs | 8 hrs | 30
| Add Comment | 8 hrs | 6 hrs | 8 hrs | 40
| Archive Project | 8 hrs | 9 hrs | 9 hrs | 50
|  |  |  | 110 hrs |  | 63